## Sheet1
| Tasks | Days | Predesscecor
1 | Pick Retro Game | 1
2 | Create Gantt Chart | 1 | 1
3 | Create Basic Movement | 2 | 1
4 | Basic Sprites | 1 | 3
5 | Create walls, floors | 1 | 4
6 | Test Game | 2 | 5
7 | Create bad guys, GUI | 2 | 6
8 | Test Game | 1 | 7
9 | Fix problems | 1 | 8
10 | Update Gantt Chart | 1 | 9
11 | Begin Level design process | 2 | 9
12 | Create annotated mockups | 3 | 9
13 | Collect sprites for level design | 2 | 11
14 | Design levels | 2 | 12
15 | Test level design | 1 | 14
16 | Make Changes | 2 | 15
17 | Finalise level design | 1 | 16
18 | Final elements- Sound, Menu | 3 | 17
19 | Create testing table | 3 | 18
20 | Finish Journal | 2 | 19
21 | Finalize Gantt chartt | 2 | 20
22 | Finish Game | 2 | 21
40